## Prod Patching
Assigned SQL Resource for Patching (14.0.3456.2 - CU31 - KB5016884) | RESOURCE GROUP | VMs | DB(s) | Status | Comments
ERCA | sap-py1-prd-rg | azsappdb32; azsappdb33 | PY1 | Complete | No issues, SQL2017 CU31 patched.
ERCA | sap-po1-prd-rg | azsappdb34; azsappdb35 | PO1 | Complete | No issues, SQL2017 CU31 patched.
ERCA | sap-ph1-prd-rg | azsappdb39; azsappdb40 | PH1 | Complete | No issues, SQL2017 CU31 patched.
ERCA | sap-ps1-prd-rg | azsappdb41; azsappdb42 | PS1 | Complete | SQL2017 CU31 patched after re-sizing azsappdb42 C Drive from 30GB to 128GB. Issue on VM: The PS1 Database on AG Instance of azsappdb41/PS1DB and azsappdb42/PS1DB is in Not-Synchronizing / In Recovery state for ~2hours after the scheduled OS Patching Reboot.
ERCA | sap-octupus-prd-rg | azsapp069 | OctopusDeploy-OctopusServer | Complete | No issues, SQL2017 CU31 patched.