## NonProd Patching
Assigned SQL Resource for Patching (14.0.3456.2 - CU31 - KB5016884) | RESOURCE GROUP | VMs | DB(s) | Status | Comments
RENZ/NKOL | sap-ss1-dev-rg | azsapd003 | SS1 | Completed | With issues - Unable to start SQL service. SQL License issue has been resolved and the CU31 patch has been executed successfully.
RENZ | sap-sd1-dev-rg | azsapd007 | SD1 | Completed | No Issues.
RENZ | sap-ye1-sbx-rg | azsapd035 | YE1 | Completed | No Issues.
RENZ | sap-ye6-dev-rg | azsapd039 | YE6 | Completed | No Issues.
RENZ | sap-ye9-dev-rg | azsapd041 | YE9DB; MSSQLSERVER | Completed | No Issues.
RENZ | sap-shared-sql-dev-rg | azsapddb04 | DA1; DK1; DBJ; D1H; D21; DR1; LMD; D11; D1L | Completed | No Issues.
RENZ | sap-shared-sql-db07-dev-rg | azsapddb07 | SG3DB; SB3DB; DG3DB; DB3DB; DE1DB; DE2DB; DO1DB; DY1DB; DXCDB | Completed | No Issues.
RENZ | sap-ds1-dsj-dev-rg | azsapddb08; azsapddb09 | DS1 | Completed | No Issues.
RENZ | sap-dl1-dev-rg | azsapddb12 | MSSQLSERVER | Completed | No Issues.
RENZ | sap-ye6-dev-rg | azsapddb13 | YE6 | Completed | No Issues.
RENZ | sap-stacking-db-development-server-dev-rg | azsapddb14 | DH1; DH2 | Completed | No Issues.
RENZ | sap-sn5-dev-rg | dkcdcsapd976 | BODS_CEN_SN5; BODS_TEST_DEV; BODS_TEST_OLBIS; BODS_TEST_SN5; DSCTRL; DSSTAGE; SN5BODS | Completed | No Issues.
RENZ | sap-qe2-tst-rg | azsapqdb01; azsapqdb02 | QE2 | Completed | No Issues.
ERCA | sap-qxc-tst-rg | azsapqdb03; azsapqdb05 | QXC | Completed | No Issues.
ERCA | sap-q11-tst-rg | azsapqdb06; azsapqdb07 | Q11 | Completed | With Issues - Repaired the azsapqdb06 instance to continue the patch. DefaultLog in Registry is incorrect - corrected the path for Log From: G:\MSSQL\Log To: G:\Microsoft SQL Server\MSSQL14.Q11DB\MSSQL\Log
ERCA | sap-q21-tst-rg | azsapqdb08; azsapqdb09 | Q21 | Completed | No Issues.
ERCA | sap-qk1-tst-rg | azsapqdb10; azsapqdb11 | QK1 | Completed | No Issues.
ERCA | sap-q1l-tst-rg | azsapqdb12; azsapqdb13 | Q1L | Completed | No Issues.
ERCA | sap-qbj-tst-rg | azsapqdb14; azsapqdb15 | QBJ | Completed | No Issues.
ERCA | sap-qb3-tst-rg | azsapqdb17; azsapqdb18 | QB3 | Completed | No Issues.
ERCA | sap-qg3-tst-rg | azsapqdb19; azsapqdb20 | QG3 | Completed | No Issues.
ERCA | sap-qe1-tst-rg | azsapqdb21; azsapqdb22 | QE1 | Completed | No Issues.
ERCA | sap-qn5-tst-rg | azsapqdb23 | MSSQLSERVER | Completed | No Issues.
ERCA | sap-qo1-tst-rg | azsapqdb24; azsapqdb25 azsapqdb28 | QO1; MSSQLSERVER | Completed | No Issues.
ERCA | sap-qy1-tst-rg | azsapqdb26; azsapqdb27 | QY1 | Completed | No Issues.
ERCA | sap-qh1-tst-rg | azsapqdb29; azsapqdb30 | QH1 | Completed | No Issues.
ERCA | sap-qh2-tst-rg | azsapqdb31; azsapqdb32 | QH2 | Completed | With Issues - Repaired the azsapqdb31 instance to continue the patch Missing Drive F: (MSSQL Data) whenever the VM is restarted. F: Drive is re-attached every VM restart for the QH2 DB Instance to be in service.

## Prod Patching
Assigned SQL Resource for Patching (14.0.3456.2 - CU31 - KB5016884) | RESOURCE GROUP | VMs | DB(s) | Status | Comments
ERCA | sap-lmp-prd-rg | azsappdb01; azsappdb02 | LMP | Completed | No Issues.
ERCA | sap-pd1-prd-rg | azsappdb07; azsappdb08 | PD1 | Completed | No Issues.
ERCA | sap-pk1-prd-rg | azsappdb09; azsappdb10 | PK1 | Completed | No Issues.
ERCA | sap-pa1-prd-rg | azsappdb11; azsappdb12 | PA1 | Completed | No Issues.
ERCA | sap-p21-prd-rg | azsappdb13; azsappdb14 | P21 | Completed | No Issues.
ERCA | sap-p11-prd-rg | azsappdb15; azsappdb16 | P11 | Completed | No Issues. Data Drive (F:) and Tempdb Drive (H:) are full, ticket logged. ITE3885100 - azsappdb15/azsappdb16 (P11DB): MSSQL Data (F:) and MSSQL Tempdb (H:) are running out of disk space. Free_MB for F Drive (MSSQL Data): 37700 InstanceName: azsappdb15\P11DB and azsappdb16\P11DB Used_Space_Percent: 95 Free_MB for H Drive (MSSQL Tempdb): 10 InstanceName: azsappdb15\P11DB Used_Space_Percent: 99
ERCA | sap-pr1-prd-rg | azsappdb17; azsappdb18 | PR1 | Completed | No Issues.
RENZ | sap-pg3-prd-rg | azsappdb19; azsappdb20 | PG3 | Completed | No Issues
RENZ | sap-p1l-prd-rg | azsappdb22; azsappdb23 | P1L | Completed | No Issues
RENZ | sap-pb3-prd-rg | azsappdb24; azsappdb25 | PB3 | Completed | No Issues
RENZ | sap-pbj-prd-rg | azsappdb26; azsappdb27 | PBJ | Completed | No Issues
RENZ | sap-pe1-prd-rg | azsappdb30; azsappdb31 | PE1 | Completed | No Issues
RENZ | sap-pxc-prd-rg | azsappdb37; azsappdb38 | PXC | Completed | No Issues