## Slide 1: IT-52167 Old-EA Migration
Kick-off

## Slide 2: Project Team
2
TOATR
Project Manager
POBLA
Business Lead
Accenture
Technical Assessment team
SEAAA
Solution Architect Lead
Azure SME
Migration team
PRAT + DAJU
Solution Architect
SABNL
FW resource

## Slide 3: Resource Plan
3
Roles | Initials | October | November | December | January | February | March
Project Manager | TOATR | 90 | 90 | 90 | 90 | 90 | 90
Business Lead | POBLA | - | - | - | - | - | -
Solution Architect Lead | SEAAA | 90 | 90 | 90 | 90 | 90 | 90
Solution Architect NNIT | DAJU | 80 | 80 | 80 | 80 | 80 | 80
Solution Architect NNIT | PRAT | 80 | 80 | 80 | 80 | 80 | 80
FW resource | SABNL | 10 | 10 | 10 | 10 | 10 | 10
Technical Assessment team | Accenture | ? | ? | ? | ? | ? | ?
Azure SME | JAHLU | 80 | 160 | 160 | 160 | 160 | 160
Azure SME | ERROE | 80 | 160 | 160 | 160 | 160 | 160
Azure SME | RALAZ | 80 | 160 | 160 | 160 | 160 | 160
Azure SME | WLJMA | 80 | 160 | 160 | 160 | 160 | 160

## Slide 4
Security:
Applications in old Enterprise Agreement constitute a security risk. To achieve security compliance migration team migration must be done to new EA in Azure.
Strategic upskilling:
Vestas needs to have skills & experience of doing cloud migrations and Azure cloud operating standard.
The major goal is to achieve security compliance for the 27 applications currently in old-EA.
Drivers:
Goals and outcomes:​
4
 | Description | Owner (initials) | Financial Value (if applicable) | From Year | To Year
1 | Security compliance by remediating all infrastructure related security alerts | SEAAA |  |  | 
2 | Security compliance by addressing all application related security alers | SEAAA |  |  | 
Benefits:
Drivers, Goals, and Benefits

## Slide 5
1) Technical assessment of the 27 applications currently in old-EA incl.
  Detailed migration planning (runbook)
  Recommendation on application related security alerts to be adressed after migration
  Plan for test activities
2) Migration of the 27 applications
Dependencies:
Application owners collaboration for
Workshops (1hr estimated, further iterations may be needed)
providing information and
addressing application security alerts
Assumptions:
Outcome of technical assessment does not reveal application related issued that needs to be fixed in advance of migration. If so, application may be rescheduled to another phase.
Migration team is competent and able to aleviate both infrastructure security alerts based on technical assessment and do the migration. The team has experience to Azure migrations, will be provided with detailed migration runbook and is supported by Azure architects.
Azure policies have been implemented in new EA.
Azure Isotope works a expected (has been installed September 26)
5
Scope and dependencies
Scope:
Dependencies and assumptions:​

## Slide 6: Project Plan
Oct
Nov
Dec
Jan
Feb
March
2022
6
Vendor dialogue​
Phase 1
Milestone
03.10.2022
Task
Technical Assessment
Project start / G1
Develop
Design
UAT
Hypercare
Go-Live
Hypercare
Project End
Accenture migration team
2023
Phase 1
Remediation of infrastructure related alerts
Migration
Phase 1
Phase 2
Phase 3
Vestas freeze December 12 – January 13
Phase 2
Phase 2
Phase 3
Phase 3
Migration team HPMO
31.03.2023

## Slide 7: Project Plan
Oct
Nov
Dec
Jan
Feb
March
2022
7
Vendor dialogue​
Phase 1
Milestone
03.10.2022
Task
Technical Assessment
Project start / G1
Develop
Design
UAT
Hypercare
Go-Live
Hypercare
Project End
Accenture migration team
2023
Phase 1
Remediation of infrastructure related alerts
Migration
Phase 1
Phase 2
Phase 3
Vestas freeze December 12 – January 13
Phase 2
Phase 2
Phase 3
Phase 3
Migration team HPMO
31.03.2023
Documented deliverables from Technical Assessment team:
Pre-migration test use cases
Recommendation to application owners on all application related alerts
Detailed migration runbook for each application
Runbook for remediation of infrastructure related alerts
Post-migration test use cases
Hypercare KT after migration
HOTO of technical assessment and migration runbook per application
How / where to document in ServiceNow
17.10.2022

## Slide 8: Project Plan
Oct
Nov
Dec
Jan
Feb
March
2022
8
Vendor dialogue​
Phase 1
Milestone
03.10.2022
Task
Technical Assessment
Project start / G1
Develop
Design
UAT
Hypercare
Go-Live
Hypercare
Project End
Accenture migration team
2023
Phase 1
Remediation of infrastructure related alerts
Migration
Phase 1
Phase 2
Phase 3
Vestas freeze December 12 – January 13
Phase 2
Phase 2
Phase 3
Phase 3
Migration team HPMO
31.03.2023
Workshop scheduling
All scheduled for phase 1
Ready for phase 2 first week of November?
Kick-off together with Migration team
Day call in Aarhus?
HOTO
How long for HOTO?
  4hrs pr application?
  A session pr application?
Migration planning
When TA team conducts workshops with AO, you also agree on Service window for migration – where do we capture this (in a template...)?
Sentia LZ delivery incl. workshp
Detail call on this later today
17.10.2022
Hyper care?
When?
Who?
How?

## Slide 9: Project Plan
Oct
Nov
Dec
Jan
Feb
March
2022
9
Vendor dialogue​
1
Milestone
03.10.2022
Task
Technical Assessment
Project start / G1
Develop
Design
UAT
Hypercare
Go-Live
Hypercare
Project End
Accenture migration team
2023
Remediation of infrastructure related alerts
Migration
2
Phase 3
Vestas freeze December 12 – January 13
Phase 2
Phase 2
Phase 3
Phase 3
Migration team HPMO
31.03.2023
Example of application A:
Notification to TOATR on service window ASAP
  Ensure to notify migration team
  Schedule handover session
  Engagement with Sentia
Workpackage hand-over
AO conduct pre-migration test
  Test result?
Migration by migration team
Remediation of infrastructure related alerts by migration team
Documentation in ServiceNow by migration team
Hypercare phase
Post-migration UAT
Hand-over of recommendation for remediation of application related security alerts to AO
17.10.2022
Remediation of infrastructure related alerts
Pre-migration test
Application owner
3
4-5-6
7
8
8

## Slide 10: Risk Analysis
Top 5 Risks
Risk ID | Description | Risk Owner | Probability (Value 1-5) | Impact (Value 1-5) | Mitigating actions
1 | Low knowledge of applications | Application owner | 4 | 4 | Owners and architects informed on info need pre-workshop.
2 | Pre-existing bugs not identified during Technical assessment. Post-migration owners will ask for fixing as part of hyper care. | SEAAA | 3 | 2 | -
3 | Critial application security alerts not being adressed by application owner | Application owner | 2 | ? | -
4 | Lack of skills (IaaC) of migration team | ALAMA | 2 | 3 | Dry-run mid-October.
5 | Firewall changes: Port openings, load balancers | SEAAA | 2 | 3 | Included SABNL in project + include FW steps in runbook.
6 | Project end later than March 31 | TOATR | 3 | 1 | Re-estimation before each phase + scheduling of workshops now

## Slide 11: Sterco pre-approval of contingency plans
Some applications are very low value, but the migration effort will be high. If Technical Assessment establish this, SEAAA is authorized to decom application.
1 Can we focus only on mature applications?
Sterco decision on most effectful way of escalation?
2 If application owners don’t collaborate
For security alerts Low and Medium SEAAA is authorized to decide that alerts are not adressed. If issues on fixing High, sterco will be notified.
4 If infrastructure security alerts are too complex to solve pre-migration
Application owners must or is strongly recommended to act in accordance with recommendation?
5 Guidance to application owners on application related security alerts
Escalation to sterco.
6 In case migration team is allocated to other tasks.
1hr workshop = no budget. If workshops needed above this, project will cover costs (hrs).
3 Application owners time for workshops

## Slide 12: Input provided at solution concept review September 23
Input from reviewers
Recommendation from project:
Further review sessions contain a risk for delay.
If an application is assessed as business critical, a review of the migration solution for that specific application will be done.

## Slide 13: Governance in ADO
Old-EA Migration team Features Backlog - Boards (visualstudio.com)